## Pandemica - Task Plan
* PHASE # - STATUS * | * TASK NAME * | * TASK DESCRIPTION * | * DUE DATE * | * ASSIGNED TO * | * TASK STATUS * | * CARD # * | * CARD URL *
General Information | Project Links | This is a quick start guide for this project's external files and links. - In Google Drive we uploaded the original technical specs of the project, referred to as CoTEC-2020. - The UI prototype for web and mobile app was made in Figma, also found in the link below. - We use GitHub for version control, throughout development it remains private, only accessible to the development team. This is made to ensure consistency and prevent other groups from stealing code. Contact Alejandro for access, as he is the administrator. Refer to "Contact information" card and "Meetings & Roles" list for more details about organization. |  |  |  | 35 | https://trello.com/c/sZ5EeDBa
General Information | Contact Information | General Team Contact Information WhatsApp: (incl. country code +506 for Costa Rica) Jose Daniel Acuña: 7024-7476‬ Kevin Cordero: 8311-5451‬ Alejandro Ibarra: 8428-0167 Jesús Sandoval: 8706-2481‬ Jose Sánchez: 8688-9864‬ Email: Jose Daniel Acuña: jodaniel1409@gmail.com Kevin Cordero: kevinscorzu@gmail.com Alejandro Ibarra: josealejandroibarra@hotmail.com Jesús Sandoval: sandoval14yamir@hotmail.com Jose Sánchez: jose.david.san@gmail.com |  |  |  | 37 | https://trello.com/c/pTNSZqEt
Roles & Meetings | Role Assignment | Jose D. Acuña - Web Functionality Manager & Design Assistant Kevin Cordero - Lead Developer on Back-end & Connections Alejandro Ibarra - Lead Designer & Mobile App Developer. Assistant Project Manager Jose D. Sánchez - Database Administration & Definition Jesús Yamir Sandoval - Project Manager & Web Developer |  |  |  | 29 | https://trello.com/c/QaNGjGWa
Roles & Meetings | Meeting Channels | Team meetings will be held using Discord, on the channel named "Régimen Corderista - Virtual Sessions". Contact any member of the team, as Discord channels are currently private only. We also have a WhatsApp group. All members are constantly checking it during the day, so don't hesitate to use this channel to ask quick questions or offer suggestions for project details. To join this group, please contact Kevin. Team contact information can be found in the "Contact Information" card. |  |  |  | 38 | https://trello.com/c/ca0Iqc0k
Roles & Meetings | Meeting One - Initial Planning |  | 2020-06-01 15:00 |  |  | 30 | https://trello.com/c/QWDF6RfL
Roles & Meetings | Meeting Two - Phase 1 Recap |  | 2020-06-05 19:00 |  |  | 31 | https://trello.com/c/Vynvt0bD
Roles & Meetings | Meeting Three - Phase 2 Discussion |  | 2020-06-12 19:00 |  |  | 32 | https://trello.com/c/p0RNBeqv
Roles & Meetings | Meeting Four - Phase 2 Recap |  | 2020-06-16 19:00 |  |  | 33 | https://trello.com/c/EniE5n1l
Roles & Meetings | Meeting Five - Phase 3 Discussion |  | 2020-06-19 15:00 |  |  | 34 | https://trello.com/c/Abm0R8TF
Roles & Meetings | Meeting Six - Final Touches |  | 2020-06-25 15:00 |  |  | 39 | https://trello.com/c/DHP6OVJs
Phase 1 - Done | Initial GitHub project organization |  | 2020-06-01 15:00 |  | green | 25 | https://trello.com/c/6dxpShoS
Phase 1 - Done | First Executive Report |  | 2020-06-05 22:00 | JM |  | 40 | https://trello.com/c/dfsKu6v5
Phase 1 - Done | Web App UI Design |  | 2020-06-04 15:00 | AI,JA | green | 8 | https://trello.com/c/YKtaM95K
Phase 1 - Done | Mobile App UI Design |  | 2020-06-05 15:00 | AI | green | 7 | https://trello.com/c/v02oFCQK
Phase 1 - Done | Initial database diagrams | Draw database diagrams | 2020-06-04 15:00 | JA,JS,JM | green | 17 | https://trello.com/c/S1YOyr44
Phase 1 - Done | Install .NET Framework |  | 2020-06-01 15:00 | KC | green | 28 | https://trello.com/c/EOslhlEn
Phase 1 - Done | Initial task plan |  | 2020-06-01 15:00 | AI,JM | green | 12 | https://trello.com/c/Ck3VHHN7
Phase 2 - Done | Web app login system |  | 2020-06-12 12:00 | JA | green | 24 | https://trello.com/c/eCkWPhew
Phase 2 - Done | Upload, parse and send Excel document data |  | 2020-06-20 12:00 | JA,JM | green | 23 | https://trello.com/c/0uUo8HNb
Phase 2 - Done | Home View for pandemic tracking | Principal view | 2020-06-19 12:00 | JA | green | 27 | https://trello.com/c/FZTgmzZq
Phase 2 - Done | Tables with restrictions | 3 tables with restrictions: - Patient Status (can only select from 3 status) - Country Sanitary Restrictions (can't delete, can disable) - Known Contacts by Patient (send an email to contact) | 2020-06-15 12:00 | JM | green | 5 | https://trello.com/c/LZaglH2H
Phase 2 - Done | Mobile App Login System | SwiftUI login system | 2020-06-11 12:00 | AI | green | 6 | https://trello.com/c/z4ITKWBU
Phase 2 - Done | Database Implementation | Define database according to relational modeling Define 5 store procedures and 2 triggers | 2020-06-10 12:00 | JS,KC | green | 20 | https://trello.com/c/Rd2EItUQ
Phase 2 - Done | Mobile App Connections and Tables | Connect table data from API in SwiftUI view | 2020-06-09 12:00 | AI | green | 10 | https://trello.com/c/gjwsMvhA
Phase 2 - Done | Mobile App Local Database | Define a local SQL Lite Core Data database in Swift following project relational diagram | 2020-06-13 12:00 | AI | green | 9 | https://trello.com/c/v72x7fkt
Phase 2 - Done | Second Executive Report |  | 2020-06-12 22:00 | JM | green | 41 | https://trello.com/c/V8ORgBU3
Phase 2 - Done | Simple tables | 5 simple tables in Admin View: - Regions - Pathologies - Health Centers - Sanitary Restrictions - Approved Drugs 1 simple table in Health Center View: - Patients | 2020-06-14 12:00 | JM | green | 4 | https://trello.com/c/UlrkW0Sn
Phase 2 - Done | Services API Design & Implementation | Define | 2020-06-14 12:00 | KC,JS | green | 18 | https://trello.com/c/ZwGz4kkp
Phase 2 - Done | Define general web app styles | Define general app styles according to the Figma prototype | 2020-06-14 12:00 | AI | green | 11 | https://trello.com/c/Xz4y6TG3
Phase 2 - Done | Third Executive Report |  | 2020-06-19 22:00 | JM | green | 42 | https://trello.com/c/MS9s3e7w
Phase 2 - Done | Organize admin and health center view |  | 2020-06-19 14:35 | JM | green | 45 | https://trello.com/c/vwEpwwtW
Phase 2 - Done | API Connections with Angular |  | 2020-06-17 15:00 | KC | green | 36 | https://trello.com/c/KSQgDbDW
Phase 2 - Done | API connections with Database |  | 2020-06-14 15:00 | JS | green | 44 | https://trello.com/c/sqZuHtjj
Phase 3 - Done | Project Delivery |  | 2020-07-03 22:00 | AI | green | 43 | https://trello.com/c/IbFNwzen
Phase 3 - Done | Project Documentation | includes log and diagrams | 2020-07-03 20:00 | JM | green | 16 | https://trello.com/c/C07Z1v70
Phase 3 - Done | Build |  | 2020-07-03 | JA | green | 46 | https://trello.com/c/YHmmadtX
Phase 3 - Done | Report generation in back-end |  | 2020-06-25 12:00 | JA,KC | green | 21 | https://trello.com/c/HoyPTtjZ
Phase 3 - Done | Update GitHub README |  | 2020-06-25 12:00 | AI | green | 26 | https://trello.com/c/nAtWvG1Q
Phase 3 - Done | User Manual & Installation Guide |  | 2020-06-25 12:00 | AI,KC | green | 15 | https://trello.com/c/P1BmkJSS
Phase 3 - Done | Report downloads in web app |  | 2020-06-24 12:00 | KC | green | 22 | https://trello.com/c/cb8iE7Ox
Phase 3 - Done | Mobile App testing |  | 2020-06-22 12:00 | AI | green | 14 | https://trello.com/c/fRB9buda
Phase 3 - Done | Full table testing |  | 2020-06-22 12:00 | JM,KC | green | 13 | https://trello.com/c/zVWEohNO

## Archived Pandemica - Task Plan
List | Title | Description | Points | Due | Members | Labels | Card # | Card URL
Phase 2 - To Do | [archived] Fase 1 |  |  |  | JM,AI | green,yellow,orange,red | 3 | https://trello.com/c/whLB1Eh0
Phase 3 - To Do | [archived] anual |  |  |  |  | red | 19 | https://trello.com/c/cagg0q4I