## Pandemica Second Wave
* PHASE # - STATUS * | * TASK NAME * | * TASK DESCRIPTION * | Points | * DUE DATE * | * ASSIGNED TO * | * TASK STATUS * | * CARD # * | * CARD URL *
General Information | Project Links | This is a quick start guide for this project's external files and links. - In the Slack channel we uploaded the original technical specs of the project, referred to as Hospital TECnológico. - The UI prototype for web and mobile app was made in Figma, also found in the link below. - We use GitHub for version control, throughout development it remains private, only accessible to the development team. This is made to ensure consistency and prevent other groups from stealing code. Contact Alejandro for access, as he is the administrator. Refer to "Contact information" card and "Meetings & Roles" list for more details about organization. |  |  |  |  | 1 | https://trello.com/c/84bCiGg8
General Information | Contact Information | General Team Contact Information WhatsApp: (incl. country code +506 for Costa Rica) Jose Daniel Acuña: 7024-7476‬ Kevin Cordero: 8311-5451‬ Alejandro Ibarra: 8428-0167 Jesús Sandoval: 8706-2481‬ Jose Sánchez: 8688-9864‬ Email: Jose Daniel Acuña: jodaniel1409@gmail.com Kevin Cordero: kevinscorzu@gmail.com Alejandro Ibarra: josealejandroibarra@hotmail.com Jesús Sandoval: sandoval14yamir@hotmail.com Jose Sánchez: jose.david.san@gmail.com |  |  |  |  | 2 | https://trello.com/c/O3d57Mu2
Roles & Meetings | Role Assignment | Jose D. Acuña - Web Functionality Manager & Design Assistant Kevin Cordero - Lead Developer on Back-end & Connections Alejandro Ibarra - Lead Designer & Mobile App Developer. Assistant Project Manager Jose D. Sánchez - Database Administration & Definition Jesús Yamir Sandoval - Project Manager & Web Developer |  |  |  |  | 3 | https://trello.com/c/sBFK9KiS
Roles & Meetings | Meeting Channels | Team meetings will be held using Discord, on the channel named "Régimen Corderista - Virtual Sessions". Contact any member of the team, as Discord channels are currently private only. Official team communication will be held in the Slack workspace schlafenhase.slack.com We also have a WhatsApp group. All members are constantly checking it during the day, so don't hesitate to use this channel to ask quick questions or offer suggestions for project details. To join this group, please contact Kevin. Team contact information can be found in the "Contact Information" card. |  |  |  |  | 4 | https://trello.com/c/82mwwvZP
Roles & Meetings | Meeting 1 |  |  | 2020-07-22 19:00 | AI,JM,JA,JS,KC |  | 25 | https://trello.com/c/iWWNdbLL
Roles & Meetings | Meeting 2 |  |  | 2020-07-24 19:00 | AI,JM,JA,JS,KC |  | 26 | https://trello.com/c/K5AJ88mX
Roles & Meetings | Meeting 3 |  |  | 2020-07-29 19:00 | AI,JM,JA,JS,KC |  | 27 | https://trello.com/c/RoZxfCmo
Roles & Meetings | Meeting 4 |  |  | 2020-07-31 19:00 | AI,JM,JA,JS,KC |  | 28 | https://trello.com/c/ekX5mdMX
Roles & Meetings | Meeting 5 |  |  | 2020-08-06 19:00 | AI,JM,JA,JS,KC |  | 29 | https://trello.com/c/IbEWFshW
Phase 1 - Done | Initial GitHub project organization |  |  | 2020-07-20 22:00 | AI |  | 7 | https://trello.com/c/cAVPTyxO
Phase 1 - Done | Web App UI Design |  |  | 2020-07-21 22:00 | AI |  | 8 | https://trello.com/c/M9DRE73v
Phase 1 - Done | Initial task plan |  |  | 2020-07-18 22:00 |  |  | 9 | https://trello.com/c/tL8ntRyS
Phase 1 - Done | 3 suggested database conceptual diagrams |  |  | 2020-07-22 22:00 | AI,JM,JA,JS,KC |  | 6 | https://trello.com/c/nSxbKOyH
Phase 1 - Done | Database relational model |  |  | 2020-07-24 22:00 | AI,JM,JA,JS,KC |  | 11 | https://trello.com/c/LNnhPG0w
Phase 2 - Done | Web App Login System |  |  | 2020-07-25 22:00 | AI |  | 13 | https://trello.com/c/eOZ0jPSe
Phase 2 - Done | Initial PostgreSQL & MongoDB database work | Define and initialize both databases. |  | 2020-07-27 22:00 | JA,JS |  | 12 | https://trello.com/c/p1TbdTUt
Phase 2 - Done | Web App Logic Programming |  |  | 2020-07-24 22:00 | JM,AI |  | 10 | https://trello.com/c/Xr7xGDp2
Phase 2 - Done | API Connections with Front End |  |  | 2020-07-31 22:00 | KC |  | 14 | https://trello.com/c/jNJfdfZ2
Phase 2 - Done | API Connections with PostgreSQL and MongoDB |  |  | 2020-07-24 22:00 | JA,JS |  | 15 | https://trello.com/c/AkpKo2fo
Phase 2 - Done | MongoDB Report in Front End |  |  | 2020-07-29 22:00 | JS,JM |  | 19 | https://trello.com/c/GL79n7Du
Phase 2 - Done | Services API Initial Implementation |  |  | 2020-07-24 22:00 | KC |  | 21 | https://trello.com/c/4SqPswNm
Phase 2 - Done | Table Upgrades in Web App |  |  | 2020-07-25 19:52 | JM |  | 30 | https://trello.com/c/ceelhMXG
Phase 3 - Done | Project Delivery |  |  | 2020-08-07 22:00 | AI |  | 5 | https://trello.com/c/Y8em8hmI
Phase 3 - Done | Update GitHub README |  |  | 2020-08-06 22:00 | AI |  | 16 | https://trello.com/c/szyN6d9w
Phase 3 - Done | Project Documentation |  |  | 2020-08-05 22:00 | JM |  | 17 | https://trello.com/c/k8RKbQT0
Phase 3 - Done | User and Deployment Manual |  |  | 2020-08-06 22:00 | AI |  | 18 | https://trello.com/c/tEsN62sD
Phase 3 - Done | Final database work |  |  | 2020-07-31 22:00 | JA,KC,JS |  | 22 | https://trello.com/c/nbhSQGPT
Phase 3 - Done | Final Services API work |  |  | 2020-08-05 22:00 | KC |  | 23 | https://trello.com/c/1bayMXbz
Phase 3 - Done | App Testing |  |  | 2020-08-05 22:00 | KC |  | 24 | https://trello.com/c/WsRlU7zI
Phase 3 - Done | Build release |  |  | 2020-08-06 22:00 | JA |  | 20 | https://trello.com/c/2rjry5ws
JA: José Acuña
KC: Kevin Cordero
JM: Jesús Morales
AI: Alejandro Ibarra
JS: Jose Sánchez

## Archived Pandemica Second Wave
List | Title | Description | Points | Due | Members | Labels | Card # | Card URL